## Introduction
This document aims to provide an alternative to Pegasystem's SmartBPM methodology in order to address perceived flaws in SmartBPM. For the author's appraisal of the methodology, please see the following blog post:
http://www.chellar.com/blog/?p=1804
About the Author
Declan Chellar is a Senior Business Analyst based in the European Union. He provides consultancy on business change initiatives, particularly those using Pegasystems’ PRPC. He has worked in IT since 1996 and primarily as an analyst since 1998 for companies such as Accenture, Knowledge Rules, Tata Consulting Services, Virtusa, Capgemini and Electronic Data Systems. Declan also has full systems lifecycle experience and has successfully delivered software as a PRPC analyst, developer and team manager. He is a member of the British Computer Society and the International Institute of Business Analysts (IIBA) and holds the following relevant qualifications:
· ISEB Diploma in Business Systems Development (specialising in Business Analysis)
· Pegasystems PRPC v6.1 Certified Business Architect
· Pegasystems Certified Methodology Black Belt
· Certified BPMN 2.0 Professional
Declan writes about his business analysis experiences on his blog “Analysis Fu” and tweets about business analysis as @AnalysisFu.
http://www.chellar.com/blog
Contact: consulting@chellar.com

## Phase Objectives
Project Initation Objectives
• Ensure that the development team gains an initial understanding of the business needs and design constraints
• Ensure that the business stakeholders gain an initial understanding of PRPC
• Ensure that all participants understand the methodology to be used
• Introduce all participants to a common project vocabulary
Project Initation Pre-requisites
• Business case
• High level statements of requirement
• High-level To Be business process models
• Logical Data Model (to ensure that the business understands its own data needs)
• High level solution design
Inception Phase Objectives
• Define the scope of the project
• Estimate the size of the work
• Identify business priorities and technical risks
• Produce an initial project plan based on business priorities and technical risks (dividing the work into several releases if necessary)
Inception Phase Pre-requisites
• All Project Initiation tasks are complete (see "Project Initiation" tab below)
Elaboration Phase Objectives
• Define low level requirements for high and (most) medium business priorities
• Mitigate key technical risks
• Establish technical architecture
• Develop and test key, high priority, business functions
• Define testing strategy
• Define deployment strategy
• Start preparing training materials
Elaboration Phase Pre-requisites
• All Inception Phase tasks are complete (see "Inception" tab below)
Construction Phase Objectives
• Complete requirements definition for medium and low business priorities
• Complete system build
• Build testing and training environments
• Complete preparing training materials
Construction Phase Pre-requisites
• All Elaboration Phase tasks are complete (see "Elaboration" tab below)
Transition Phase Objectives
• Deploy system into testing and training environments
• Complete system-wide testing (e.g., performance, integration, user acceptance)
• Complete preparing training materials
• Deliver training to end users
• Deliver training to maintenance team
Transition Phase Pre-requisites
• All Construction Phase tasks are complete (see "Construction" tab below)
Go Live Objectives
• Deploy system into production environment
• Complete handover to maintenance team
• Monitor production system
Go Live Pre-requisites
• All Transition Phase tasks are complete (see "Transition" tab below)

## Roles
ROLE | DESCRIPTION | NOTES
Cust | Customer | This represents the customer in the broad sense, including: • Business sponsors • Business stakeholders • Enterprise architects • Solutions architects
BA | Business Analyst | Represents any BAs working on the project. There may be two types of BA on your project: • Business specialist • PRPC specialist
PM | Project Manager | This role may be in charge of an entire programme cutting across technology teams or in charge of the PRPC effort only.
LSA | Lead Systems Architect | A Pega-certified Lead Systems Architect
SA | System Architect | A developer conversant with PRPC
QA | Quality Assurance | This represents both the Testing Manager and the testing team.
Train | Training | This represents the team responsible for rolling out the change initiative to the end users.
Maint | Maintenance | This represents the team responsible for system maintenance after deployment to production. This team may include several of the roles listed above

## Project Initiation
ACTIVITIES |  |  |  | RACI
Task | Objective | Tool Options | Deliverable | Cust | BA | PM | LSA | SA | QA | Train | Maint
Present summary of business case | Ensure all stakeholders understand strategic objectives and key risks | None specified | · The presentation itself | A/R | I | I | I | - | I | I | -
Present high level statements of requirement | Ensure all stakeholders understand the project scope | None specified | · The presentation itself | A/R | I | I | I | - | I | I | -
Present the To Be business process | Ensure all stakeholders have a vision of the process to be implemented | None specified | · The presentation itself | A/R | I | I | I | - | I | I | -
Present the high level solution design | Ensure all stakeholders understand what is to be implemented using PRPC and what interfaces will be required | None specified | · The presentation itself | A/R | I | I | I | - | I | I | -
Develop a Proof of Concept where necessary | Demonstrate that PRPC is the appropriate tool | None specified | · Proof of Concept | C | C | A/I | R | - | - | - | -
Present methodology | Ensure all stakeholders understand the methodology to be used | None specified | · The presentation itself | I | I | A/R | I | - | I | I | -
Enable training (e.g., PRPC, process modelling, use case modelling, data modelling) | Ensure all project participants have the necessary skills | None specified | · The training itself | A/R | I | I | I | I | I | I | I
Produce a project roadmap | Ensure all stakeholders understand the likely lifetime of the project and the key milestones | None specified | · Project roadmap | C | I | A/R | I | I | I | I | -
Produce a high-level staffing model | Ensure all stakeholders understand what staffing is likely to be needed | None specified | · Staffing model | C | C | A/R | C | - | C | - | -
Plan Inception workshops | Ensure necessary time for Inception is planned and participants are available | None specified | · Inception workshop plan | C | R | A/C | I | I | I | I | I
Define requirements traceability model | Ensure all stakeholders understand how requirements are to be traced | None specified | · Requirements Traceability Matix | A | R | I | I | I | I | -I | -
Document project risks | Ensure all stakeholders understand project risks and their mitigations | None specified | · Risk log | C | C | A/R | C | - | C | C | -
Document assumptions | Ensure assumptions are clear to all stakeholders | None specified | · Assumptions log | C | C | A/R | C | - | C | C | -

## Inception
ACTIVITIES |  |  |  | RACI
Task | Objective | Tool Options | Deliverable | Cust | BA | PM | LSA | SA | QA | Train | Maint
Document high level requirements | Formally establish scope and ensure HLRs are located in a central location for ease of reference | · Requirement Rule | · Requirements artefact (see Tool Options) | C | R | A/I | I | I | I | I | I
· Application Profile Wizard
· Word
· Excel
· Industry-standard requirements tools
Identify candidate software use cases (SUCs), including Actors, for high level functional requirements | Establish placeholders for further requirements analysis | · Use Case Rule | · Documented SUCs (high level) | C | R | A/I | I | I | I | I | I
|  | · Application Profile Wizard | · Documented Actors
· Word
· Industry-standard UC tools
Identify candidate business work types | Enable the LSA to define candidate PRPC work types | None specified | None specified | C | R | A/I | I | I | I | I | I
Define candidate PRPC work types | Gain an initial understanding of the PRPC class structure | · PRPC Work Type | · Documented PRPC Work Types | I | I | A/I | R | I | I | I | I
· Application Profile Wizard
Identify interface constraints | Ensure that technical risks can be identified | · Application Profile Wizard | · Documented interfaces (high level) | C | I | A/I | R | I | I | I | I
· Word
· Excel
Identify reporting requirements | Ensure reporting needs are understood at the high level | · Application Profile Wizard | · Documented reporting requirements (high level) | C | R | A/I | I | I | I | I | I
· Word
· Industry-standard requirements tools
Identify correspondence requirements | Ensure correspondence needs are understood at the high level | · Application Profile Wizard | · Documented correspondence requirements (high level) | C | R | A/I | I | I | I | I | I
· Word
· Industry-standard requirements tools
Identify business priorities | Ensure business need is understood | · Requirement Rule | · Documented business priorities | C | R | A/I | I | I | I | I | I
· Use Case Rules
· Application Profile Wizard
· Word
· Excel
· Industry-standard requirements tools
Identify technical risks | Ensure technical risks are understood | · Requirement Rule | · Documented technical risks | C | I | A/I | R | I | I | I | I
· Use Case Rules
· Application Profile Wizard
· Word
· Excel
· Industry-standard risk-management tools
Present business needs overview to stakeholders | Confirm that business needs have been understood | · Word | · Documented business needs | C | R | A/I | I | I | I | I | I
|  | · Application Profile Wizard | · PRPC Application Profile document
Estimate analysis effort | Contribute to project plan | None specified | · Analysis estimates | I | R | A/I | I | - | - | - | -
Estimate development effort | Contribute to project plan | None specified | · Development estimates | I | - | A/I | R | - | - | - | -
Estimate testing effort | Contribute to project plan | None specified | · Testing estimates | I | - | A/I | - | - | R | - | -
Estimate deployment effort | Contribute to project plan | None specified | · Deployment estimates | I | - | A/I | R | - | - | - | -
Estimate training effort | Contribute to project plan | None specified | · Training estimates | I | - | A/I | I | - | - | R | -
Complete phase readiness checklist | Ensure that Inception tasks have been satisfactorily completed | None specified | · Phase readiness checklist | I | R | A/R | R | - | - | - | -
Produce initial project/release plan | Prepare for “Go/No Go” decision for the project | · Any project planning tool | · Project plan | I | C | A/R | C | C | C | C | -
· PMF
Present project/release plan to stakeholders | Obtain “Go/No Go” decision for the project | · Any project planning tool | · Go/No Go decision | C | I | A/R | I | I | I | I | I
· PMF

## Elaboration
ACTIVITIES |  |  |  | RACI
Task | Objective | Tool Options | Deliverable | Cust | BA | PM | LSA | SA | QA | Train | Maint
Elaborate requirements | Define 80% of requirements by end of Elaboration | · Workshops | · Approved low-level requirements | C | R | A/I | C | C | C | I | -
· “Show and Tell”
· Use Case Rule
· Word
· Excel
Set up development environment | Ensure work can proceed following “Go” decision | None specified | · Development environment | - | - | A/I | R | I | - | - | -
Define Class Structure | Establish technical architecture | None specified | · Class structure | - | - | A/I | R | R | - | - | -
Build Physical Data Model | Establish technical architecture | None specified | · Physical Data Model | - | - | A/I | R | I | - | - | -
Define design principles | Ensure robust and consistent development | None specified | · Design principles | - | - | A/I | R | I | - | - | -
Establish governance model | Ensure robust and consistent development | None specified | · Governance model | - | - | A/I | R | I | - | - | -
Conduct design review | Ensure solution meets satisfies customer’s design principles and satisfies business needs | None specified | · Approved design | C | C | A/I | R | I | I | - | -
Mitigate key technical risks | Ensure “show-stoppers” are dealt with early | None specified | Depends on the nature of the risks. | - | - | A/I | R | R | - | - | -
Build business critical functionality (including supporting features, e.g., interfaces) | Early risk mitigation | None specified | · Business critical functionality | - | - | A/I | R | R | - | - | -
Unit and Function test business critical functionality | Early risk mitigation and quality assurance | · Test Management Framework | · Business critical functionality | - | - | A/I | I | R | - | - | -
· Any standard testing tools
· “Show and Tell”
Build critical technical requirements | Early risk mitigation. | None specified | · Business critical functionality | - | - | A/I | R | R | - | - | -
Unit and Function test critical technical requirements | Early risk mitigation and quality assurance. | · Test Management Framework | · Business critical functionality | - | - | A/I | I | R | - | - | -
· Any standard testing tools
· “Show and Tell”
Track and fix defects | Prepare for “Go/No Go” decision for the Construction phase | · Any project planning tool | · Project plan | I | C | A/R | R | R | R | - | -
· PMF
Define testing strategy | Prepare for wring test scripts and test environment building. | None specified | · Testing strategy | - | - | A/I | - | - | R | - | -
Define deployment strategy | Ensure strategy is defined in advance of deployment to other environments. | None specified | · Deployment strategy | - | - | A/I | R | I | - | - | -
Start producing training material | Ensure training material is ready in time for Transition phase. | None specified | · Training material | C | C | A/I | - | - | - | R | -
Re-estimate remaining analysis effort | Contribute to project plan | None specified | · Analysis estimates | I | R | A/I | I | - | - | - | -
Re-estimate remaining development effort | Contribute to project plan | None specified | · Development estimates | I | - | A/I | R | - | - | - | -
Re-estimate remaining testing effort | Contribute to project plan | None specified | · Testing estimates | I | - | A/I | - | - | R | - | -
Re-estimate deployment effort | Contribute to project plan | None specified | · Deployment estimates | I | - | A/I | R | - | - | - | -
Re-estimate remaining training effort | Contribute to project plan | None specified | · Training estimates | I | - | A/I | I | - | - | R | -
Complete phase readiness checklist | Ensure that Elaboration tasks have been satisfactorily completed | None specified | · Phase readiness checklist | I | R | A/R | R | R | R | R | -
Produce revised project/release plan | Prepare for “Go/No Go” decision for the Construction phase | · Any project planning tool | · Project plan | I | C | A/R | C | C | C | C | -
· PMF
Present revised project/release plan to stakeholders | Obtain “Go/No Go” decision for the Construction phase | · Any project planning tool | · Go/No Go decision | C | I | A/R | I | I | I | I | I
· PMF

## Construction
ACTIVITIES |  |  |  | RACI
Task | Objective | Tool Options | Deliverable | Cust | BA | PM | LSA | SA | QA | Train | Maint
Complete requirements definition | Define 100% of requirements by end of Construction | · Workshops | · Approved low-level requirements | C | R | A/I | C | C | C | I | -
· “Show and Tell”
· Use Case Rule
· Word
· Excel
Build remaining business functionality (including supporting features, e.g., interfaces) | Complete system build | None specified | · Business critical functionality | - | - | A/I | R | R | - | - | -
Unit and Function test remaining business functionality | Complete system build | · Test Management Framework | · Business critical functionality | - | - | A/I | I | R | - | - | -
· Any standard testing tools
· “Show and Tell”
Build remaining technical requirements | Complete system build | None specified | · Business critical functionality | - | - | A/I | R | R | - | - | -
Unit and Function test remaining technical requirements | Complete system build | · Test Management Framework | · Business critical functionality | - | - | A/I | I | R | - | - | -
· Any standard testing tools
· “Show and Tell”
Build test scripts for automated testing | Preparation for test execution | · Any approved automated testing tools | · Automated test scripts | - | C | A/I | I | I | R | - | -
Track and fix defects | Quality assurance | · Test Management Framework | · Project plan | C | C | A/I | R | R | R | - | -
· Any approved testing tools
· “Show and Tell”
Build testing and training environments | Prepare for Transition phase | None specified | · Testing and training environments | I | - | A/I | R | R | C | -
Complete training materials | Ensure training material is ready in time for Transition phase. | None specified | · Training material | C | C | A/I | - | - | - | R | -
Re-estimate remaining testing effort | Contribute to project plan | None specified | · Testing estimates | I | - | A/I | - | - | R | - | -
Re-estimate deployment effort | Contribute to project plan | None specified | · Deployment estimates | I | - | A/I | R | - | - | - | -
Re-estimate remaining training effort | Contribute to project plan | None specified | · Training estimates | I | - | A/I | I | - | - | R | -
Produce revised project/release plan | Prepare for “Go/No Go” decision for the Transition phase | · Any project planning tool | · Project plan | I | C | A/R | C | C | C | C | -
· PMF
Complete phase readiness checklist | Ensure that Construction tasks have been satisfactorily completed | None specified | · Phase readiness checklist | I | R | A/R | R | R | R | R | -
Present revised project/release plan to stakeholders | Obtain “Go/No Go” decision for the Transition phase | · Any project planning tool | · Go/No Go decision | C | I | A/R | I | I | I | I | I
· PMF

## Transition
ACTIVITIES |  |  |  | RACI
Task | Objective | Tool Options | Deliverable | Cust | BA | PM | LSA | SA | QA | Train | Maint
Deploy to testing and training environments | Enable test execution | None specified | Software deployed to testing and training environments | I | - | A/I | R | R | I | I
Complete system-wide testing | Quality assurance | · Any approved testing tools | · Test results | C | C | A/I | C | C | R | - | -
Track and fix defects | Quality assurance | · Test Management Framework | · Test results | C | C | A/I | R | R | R | - | -
· Any approved testing tools
· “Show and Tell”
Deliver training to end users | Business readiness | None specified | · The training itself | C | - | A/I | - | - | - | R
Deliver training to maintenance team | System support readiness | None specified | · The training itself | C | - | A/I | R | R | - | - | I
Complete phase readiness checklist | Ensure that Transition tasks have been satisfactorily completed | None specified | · Phase readiness checklist | I | I | A/R | R | R | R | R | -
Produce revised project/release plan | Prepare for “Go/No Go” decision for Go Live | · Any project planning tool | · Project plan | I | C | A/R | C | C | C | C | -
· PMF
Present revised project/release plan to stakeholders | Obtain “Go/No Go” decision for Go Live | · Any project planning tool | · Go/No Go decision | C | I | A/R | I | I | I | I | I
· PMF

## Go Live
ACTIVITIES |  |  |  | RACI
Task | Objective | Tool Options | Deliverable | Cust | BA | PM | LSA | SA | QA | Train | Maint
Migrate data into Production environment | Production readiness | None specified | · Migrated data | C | - | A/I | R | R | - | - | I
Deploy application into Production environment | Production readiness | None specified | · Deployed application | C | - | A/I | R | R | - | - | I
Perform handover to maintenance team | Production readiness | None specified | · All related business and technical documentation | I | - | A/I | R | R | - | - | I
Monitor system to identify process improvements, enhancements, etc. | Ongoing improvement | None specified | · Improvement proposals | C | C | - | - | - | - | - | A/R
Maintain application | Ongoing improvement | None specified | · Enhancements, fixes, etc. | C | - | - | - | - | - | - | A/R