Change Control Process

Version: 1.0

Date: 04/05/2008

Author: Declan Chellar

Contents

0.	Document Control	3

0.1.	Document Revision Chart	3

0.2.	Changes since last sign-off	3

0.3.	References	3

0.4.	Glossary and Acronyms	4

1.	Introduction	5

1.1.	Document Purpose	5

1.2.	Document Scope	5

1.3.	Assumptions	5

1.4.	Risks	5

1.5.	Constraints/Dependencies	5

2.	The Process	6

2.1.	Introduction	6

2.2.	Roles	6

2.3.	Change Request/Proposal Statuses	6

2.4.	Pre-conditions	7

2.5.	Tasks	7

2.6.	Post-conditions	8

2.7.	Business Rules	9

2.7.1.	A CR may be cancelled at the Requestor’s request at any point up to the baselining of the changed product(s).	9

2.7.2.	The Change Control Status Report will be issued at the end of each calendar month.	9

2.7.3.	If the Severity is not “Critical”, Urgency may not equal “Yes”.	9

2.8.	Change Control Process Flow	10

2.9.	CR Cancellation Flow	11

3.	Appendices	12

3.1.	Appendix A – CR Attributes	12

3.2.	Appendix B – Severity Table	13

4.	Sign-Off	14

# Document Control

## Document Revision Chart

The following table lists the revisions made to this document tracked by specification version. Use this to describe the changes and additions each time this document is re-published (both draft and final). The description should include as many details of the changes as possible.

| #.# | Section Modified and Revision Description | Date | Author |
| --- | --- | --- | --- |

## Changes since last sign-off

The following table summarizes each change since the document was last signed off.

| Section | Change | Reason |
| --- | --- | --- |

## References

The following table summarizes each change since the document was last signed off.

| Ref | Title | Version | Location |
| --- | --- | --- | --- |

## Glossary and Acronyms

| Term | Meaning |
| --- | --- |
| CCB | Change Control Board |
| CCP | Change Control Process |
| Change Proposal (CP) | An item that a stakeholder from the information technology services supplier has submitted to the change control process that describes a software problem, a requested enhancement, a proposed change in requirements for a product under development, or a new project being proposed. |
| Change Request (CR) | An item that a stakeholder from the Business has submitted to the change control process that describes a software problem, a requested enhancement, a proposed change in requirements for a product under development, or a new project being proposed. |
| Stakeholder | Someone who is affected by or who can influence the project. |

# Introduction

## Document Purpose

This document describes the process by which changes to baselined products can be requested and managed.

## Document Scope

This document covers only the Change Control Process. It does not cover any other processes.

## Assumptions

None.

## Risks

None.

## Constraints/Dependencies

None.

# The Process

## Introduction

This process will facilitate communication about requested changes among the stakeholders of any project, provide a common process for resolving requested changes and reported problems, and reduce the uncertainty around the existence, state, and outcome of a change that has been requested in a work product.

## Roles

| Role | Description |
| --- | --- |
| Change Manager | Chairperson of the change control board; has final decision-making authority if the CCB does not reach agreement; asks someone to be the Evaluator for each CR and asks someone to be the Modifier for each approved CR. |
| Change Control Board (CCB) | The group that decides to approve or reject CRs/CPs for a specific project. |
| Evaluator | The person whom the CCB Chair asks to analyze the impact of a CR. |
| Modifier | The person assigned responsibility for making changes in a work product in response to an approved CR. |
| Requestor | The person who submits a new CR. |
| Project Manager | The person responsible for overall planning and tracking of the development project activities. |
| Requirements Manager | The person responsible for managing the requirements on any project. |

## Change Request/Proposal Statuses

| Status | Description |
| --- | --- |
| Approved | The CCB has decided to implement the CR and allocated it to a specific future build or product release. |
| Assigned | The Change Manager has assigned the CR to an Evaluator or Evaluators for impact analysis. |
| Canceled | The Requestor has decided to cancel the CR. |
| Completed | The change made has been verified, the modified work products have been released and the CR is now completed. |
| Evaluated | All impact analyses of the CR have been made. |
| Pending Verification | The Modifier has completed implementing the CR and the change is to be reviewed by the Requestor. |
| Rejected | The CCB has decided not to implement the CR. |
| Submitted | The Requestor has submitted a new CR to the change control process. |
| Verified | The Requestor has confirmed that the modifications in affected work products were made correctly. |

## Pre-conditions

Change Control Board is established for the project.

Baselined work products exist.

## Tasks

| Task | Responsibility |
| --- | --- |
| Submit a CR to the Change Manager (flagged “Urgent” as appropriate). | Requestor |
| Log each submitted CR. | Change Manager |
| For each non urgent CR, assign at least one evaluator. For example, a change to a requirements document will require only one Evaluator (e.g., Requirements Manager). A software change will require at least two Evaluators as there will be changes to the requirements documentation, changes to the software itself and changes to the testing documentation. | Change Manager |
| For each urgent CR, call extraordinary meeting of CCB. | Change Manager |
| Estimate the number of hours of effort required to make the change. Inform the CM of the estimate. | Evaluator |
| Collate all evaluations for each CR. | Change Manager |
| Review the collated evaluation of the CR and decide whether to approve or reject it. | Change Control Board |
| Review the urgent CR and decide whether to approve or reject it. | Change Control Board |
| Where a CR has been approved, decide the timing of the change. For example, a change may be implement as part of the current release, as part of a future, planned release or as part of an unplanned enhancement release. | Change Control Board |
| Inform the Requestor of the CCB’s decision. | Change Manager |
| Where a CR has been approved, assign at least one Modifier to make the changes. Inform Requestor and PM that Modifiers have been assigned. | Change Manager |
| Where a CR has been approved, modify the Project Plan. | Project Manager |
| Make the changes. Inform the CM that the change has been made, providing actual hours of effort. | Modifier |
| Inform Requestor and PM that the changes are ready to be verified. | Change Manager |
| Review changes. Inform CM of outcome of review. | Requestor |
| Inform Modifier(s) and PM of outcome of review. | Change Manager |
| If changes are not correct, correct the changes. If changes are correct, release baselined product. Inform CM of actions. | Modifier |
| Inform Requestor, PM and Requirements Manager that baselined product has been released. | Change Manager |
| Update Requirements Traceability Matrix. | Requirements Manager |
| If the CR is no longer required, inform the CM. | Requestor |
| Maintain the status of the CR at every stage. | Change Manager |
| Generate a Change Control Status Report. | Change Manager |

## Post-conditions

The status of the CR is either:

Completed

Rejected

Cancelled

The baselined, modified products have been correctly installed into the appropriate locations.

Requirements Traceability Matrix has been updated.

## Business Rules

### A CR may be cancelled at the Requestor’s request at any point up to the baselining of the changed product(s).

### The Change Control Status Report will be issued at the end of each calendar month.

### If the Severity is not “Critical”, Urgency may not equal “Yes”.

## Change Control Process Flow

## CR Cancellation Flow

# Appendices

## Appendix A – CR Attributes

| Field | Set By | Contents |
| --- | --- | --- |
| Actual Effort | Modifier | Actual hours of effort needed to implement the change. |
| Description | Requestor | Free-form text description of the change being requested. This cannot be changed after it is entered. If citing a reported problem, enter the Problem ID as well as the text of the problem report. |
| Date Submitted | CM | Date the CR was submitted. |
| Date Updated | CM | Date the CR was most recently updated. |
| Effort Summary | Modifier | Summary description of the effort required to implement the change. |
| Estimated Effort | Modifier | Estimated hours of effort needed to implement the change. |
| ID | CM | Sequence number assigned to the CR. |
| Issue Type | Requestor | Type of change request being created: Problem fix, Enhancement, Requirement Change, New Requirement. |
| Modifier | CCB Chair | Person who is assigned responsibility for implementing the change. |
| Originator | Requestor | Requestor’s name. |
| Originator E-Mail | Requestor | Requestor’s e-mail address. |
| Originator Phone | Requestor | Requestor’s phone number. |
| Planned Release | CM | Product release number for which this approved change is scheduled. Determined by CCB. |
| Priority | CM | Relative importance of making the change: Low, Medium, High, Critical. Determined by CCB. |
| Product | Requestor | Name of the product or project in which a change is being requested or a problem reported. |
| Severity | Requestor | Severity of the change (see Appendix B). |
| Responses | CM | Free-form text of responses made to the change request by various parties. Multiple responses can be made over time. Do not change existing responses. |
| Status | CM | Update current status of the change request as it moves through the process. |
| Title | Requestor | One-line description of the issue. |
| Urgent? | Requestor | Flag indicating whether the CR is urgent. |

## Appendix B – Severity Table

| Severity | Examples |
| --- | --- |
| Minor | Cosmetic issue Usability improvement Unclear error messages Customer can live with the issue (default) |
| Major | Issue adversely affects product functioning, but a workaround is available Customer will be dissatisfied Serious usability impairment Issue blocks some testing. |
| Critical | Product does not function at all or crashes The wrong results are generated Further testing of the application is not possible |

# Sign-Off

| Signature | Name and Title | Date |
| --- | --- | --- |